## Sheet1
| HREiR Action plan template (2020-2022) | Reporting against actions coded 'As previous action' in column I. Completed actions were reported against at the 10-year review. |  |  |  | Add institutional logo
Details
| Institution name: | The University of Salford | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 1 | Audience (beneficiaries of the action plan) | Number of | Comments
| Date of submission: | 2022-09-23 | Research staff | 27
| Institutional context: | The University of Salford was one of the first UK universities to participate in the HR Excellence in Research Award, first receiving this in 2010. Our recent focus, through the University’s People Plan 2020+ has been on three areas, where we have made notable changes and improvements: 1) Ensuring wellbeing is at the heart of everything we do; 2) Developing a more inclusive and diverse place to work and study; 3) Deliberately focusing on development, performance, reward and recognition for all. Recently, there have been significant changes for our research strategy and support. In July 2021 we launched the University of Salford Innovation Strategy 2021-26, which sets out our goals for research, knowledge exchange and enterprise success and leadership, and unifies our activities under the banner of innovation. Over the strategy period we will deliver on 5 priority areas, two of which explicitly relate to our commitment to the Concordat: ‘Developing creative research and enterprise leaders’ and ‘Transforming our culture’. To support the delivery of our strategy we have created a new directorate of Research & Enterprise (R&E), supported by our Pro-Vice Chancellor Research and Enterprise. Our action plan for 2022-25 is aligned to this future vision allowing us to revisit and refresh several areas, continuously improving the support for our researchers. | Postgraduate researchers | 604
|  |  | Research and teaching staff | 838
|  |  | Teaching-only staff | 791
|  |  | Technicians | 50
|  |  | Clinicians | 0
|  |  | Professional support staff | 1248
|  |  | Other (please provide numbers and details): | 4 | Academic staff that are neither research or teaching
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Action carried over from previous action plan? | Old Concordat principle and clause | Update / Comments and reflections
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | You said, we did campaign and webpage/intranet pages. A new external website and internal Sharepoint capability means this is now more visible. | A week-long campaign to focus on personal and professional development will draw attention to the Concordat and a series of research development initiatives such as mentoring and workshops are scheduled at the end of January. This will link into the 'you said, we did' approach and will include a personalised direct communication to every member of research staff. How it will be measured: The campaign will include a short survey to identify what researchers know about the Concordat and areas that need addressing. We aim to get a 10% take up of the survey or greater and will use the feedback to help shape future interventions and campaigns. This project will run between January and April 2021 | 2021-01-01 | Researcher Developer Manager | The campaign occurred in January 2021 and gathered feedback from attendees regarding their needs. | Feedback from workshops related to more career development opportunities and mentoring. | As previous action | New | Completed - no further action
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | Annually reviewed through, PGR forum, research development group. AS group, REC and AEC. | The commitment of the Concordat and that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers is embedded in continuously assessed with the Researcher Development Group and PGR Forum responsible for monitoring and review. This will be measured annually and reviewed every 12 months as annual items of business and as part of current annual evaluation processes. The research community receive regular communications on a monthly basis or more frequently through Teams group and individual emails. | Ongoing (BAU) | Inclusion & Diversity Manager (HR), Director of the Doctoral School, Governance & Policy Manager (R&E) | Completed, the processes are established and in place. | Completed. This annual schedule and annual item of business ensures that the Concordat remains central to the research strategy and sub strategies such as researcher development and the University's People plan. Sub-groups and task and finish teams may also feed into this for completion of specific projects and streams. | Completed | P2.1 P6.8 | Completed - no further action
ECI 3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | Developed a wellbeing concordat to set out our objectives to support researchers. A wellbeing programme has been embedded into the training and development offer that includes activities such as regular wellbeing interventions, failure Friday, craft social and coffee breaks online. The introduction of an annual leave entitlement for PGRs further supports this. | Develop a specific strategy to support the wider research community and fed into the UoS wellbeing groups and development plan. This is to be in place by Sept 2021 and the training offer to continue to have a wellbeing element freely accessible to researchers and reviewed annually. Review and update of the University of Salford’s Whistleblowing policy to ensure to the highest standard of ethics, openness, probity and accountability owned by the Director of Legal and Compliance. | 2022-09-01 | HR | UoS wellbeing group is established and research Concordat in place - this has been reviewed and a new programme to support wellbeing is now embedded. The Whistleblowing policy has been revised with focus on sensitive issues, such as harassment or malpractice, can be difficult to speak about but these can still be addressed in confidence by email to a new confidential email: whistleblowing reports@salford.ac.uk. https://testlivesalfordac.sharepoint.com/sites/UoS_Staff/SitePages/Updates%20to%20University%20Whistleblowing%20policy.aspx | Completed. The University wellbeing strategy and process that link to the three year plans and development plans all contribute to the wider promotion of wellbeing at the University. The outcome is a better supported researcher community and reduction in complaints, sickness and other wellbeing indicators. However, we acknowledge that this may take longer to reflect in these indicators as Covid has had an impact on all employees and students by increasing awareness but also in seeing an increase inwellbeing related concerns. | Completed | P6.9 | Completed - no further action
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | Suite of online compulsory training for all new staff and and PGRs have been developed. Additional projects with our Quality Enhancement Office have reviewed our training, regulations and code of conduct to clarify requirements and enhance support to PGRs and staff. The University has also introduced a Proofreading and Plagiarism guidance document for all supervisors and PGRs. | The compulsory training on equality, diversity, wellbeing and mental health to be mandatory for all new researchers to complete by Oct 2021. This will be added and embedded in to the supervisory training refresher (supervisors complete the training as part of a 3 year cycle) in-line with other UoS management-level training for PSS staff by January 2022. | October 2021 | HR, Researcher Development Manager | Completed. Compulsory training in place for all new researchers. | Suite of online compulsory training for all new staff have been developed. Additional projects with our Quality Enhancement Office have reviewed our training, regulations and code of conduct to clarify requirements and enhance support. | As previous action | P2.3 | Completed - no further action
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | This has been included in the new ethics course that's compulsory for all new researchers. The Academic Ethics Committee, Research and Enterprise Committee, PGR Forum, Doctoral School Steering Group, research Development Group, and SPARC organising committee, all contribute to positive policy developments and is an annual item of business on each of the committees agendas. | Completion is monitored for staff and for PGRs at induction. The completion and content of the compulsory courses to be reviewed every 12 months and enhancement to be added such as best practice publishing and guidance on avoiding self-plagiarism. | Ongoing (BAU) | Governance and Policy Manager (R&E) | Completed. | Completed. This annual schedule and annual item of business ensures that the Concordat remains central to the research strategy and sub strategies such as researcher development and the University's People plan. Sub-groups and task and finish teams may also feed into this for completion of specific projects and streams. | Completed | P6.1 | Completed - no further action
ECI 6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | Through student and staff annual surveys, regular audits and reviews. | An annual training and development activity review is conducted each year that looks at both in-respon and online engagement with training and development opportunities. A 'suggestion box' and open door policy facilitate more regular and-hoc feedback as appropriate. Each activity has a form of evaluation embedded into it (this includes user/stakeholder consultation, feedback forms, reflective review) aiming to achieve 50% completion of evaluations. | Ongoing (BAU) | R&E (Director, Researcher Development Manager, Doctoral School) | Completed. The activity is reviewed annually. | Completed. This annual schedule and annual item of business ensures that the Concordat remains central to the research strategy and sub strategies such as researcher development and the University's People plan. Sub-groups and task and finish teams may also feed into this for completion of specific projects and streams. | Completed | New | Completed - no further action
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | This is part of the research development provision, working with funders and students to co-create an accessible model. | Continue to work with funding organisations (including industry, research councils, charities and consortiums to co-create a positive research culture and environment). This includes regular consultation with the research community and partner funders to take place on an annual basis. This will feed into a research development training programme that focuses on developing funding opportunities and collaboration aiming to achieve 30% participation across the researcher community. | July 2022 | RKE and Collaborative partners | Initial meetings took place as part of the 2018 and 2019 Festival of Research. This included the development of a Future of Research output publication: Reimagining: https://usir.salford.ac. uk/49241/. The 2020 event was postponed by Covid but will continue in 2022 either in person or as an online event | Some activity has been affected by Covid - a more specific action supercedes this. | As previous action | P6.6 | Partially completed - superceded by new action against this principle
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | This is part of our ongoing discussion with funding providers and links with actions ECI 3, ECF1 and ECF3. | Working with the research community and partners to develop a series of listening events to inform the wellbeing and different ways of working. This will then be embedded into the annual training and development cycle and aim to increase participation and engagement by 20%. | July 2022 | RKE and Collaborative partners | Initial meetings took place as part of the 2018 and 2019 Festival of Research. This included the development of a Future of Research output publication: Reimagining: https://usir.salford.ac. uk/49241/. The 2020 event was postponed by Covid but will continue in 2022 either in person or as an online event | Some activity has been affected by Covid - action discontinued due to reprioritisation of work in line with Innovation Strategy 2021-26. | As previous action | New | Action discontinued - not currently prioritised for 22-25 due to focus on outcomes of our Research Culture review
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | This is part of our ongoing discussion with funding providers and links with actions ECI 3, ECF1 and ECF2. | Continue to consult with the research community on the opportunities and strategies to increase access and equity. For example, where small grant funding is provided, revise the process so that grant applications are assessed blindly. | July 2022 | RKE and Collaborative partners | Initial meetings took place as part of the 2018 and 2019 Festival of Research. This included the development of a Future of Research output publication: Reimagining: https://usir.salford.ac. uk/49241/. The 2020 event was postponed by Covid but will continue in 2022 either in person or as an online event | Some activity has been affected by Covid - action discontinued due to reprioritisation of work in line with Innovation Strategy 2021-26. | As previous action | P6.6 | Action discontinued - not currently prioritised for 22-25 due to focus on outcomes of our Research Culture review
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | A reflective action plan is included in all of the compulsory training and researchers are encouraged to reflect on this regularly as part of the SER and 3 year plan process. | A reflective action plan is to be embedded into the new Academic Ethics training module and links to further development opportunities. The plan is designed to help researchers reflect on practice within their research and encourage regular discussion with their line manager or supervisory team; aiming to achieve 80% completion of plans cross the community. The Doctoral School is now part of the University Diversity and Equality Committee where policy and practice are reviewed annually. | Ongoing (BAU) | Researcher Development Manager | As ECI4. Online training modules available and each school/directorate is working to achieve KPIs set out in their Inclusion & Diversity action plans. | Completed. Now embedded into the current processes and is ongoing activity. | As previous action | New | Completed - no further action
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | This is embedded within the compulsory academic ethics training. | The action plans embedded within the compulsory academic ethics training, regular Q&A drop-in sessions and monitoring of completion of compliance training helps to ensure this, with a 90% pass threshold required on compliance courses and aiming for 80% completion by the researcher community.The training provides researchers with an action plan and portfolio of reflective practice to continue their development, refer to regularly and use as a framework to support professional conduct. All training is completed initially once initially and revisited annually. | September 2020 | R&E (Governance & Policy team) | Completed. | Completed. Now embedded into the current processes. The actions plans provide realistic outputs and examples of practice that can be utilised as part of the training or sharing practice within the researcher community. | Completed | New | Completed - no further action
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | Open conversations and visibility of support resources to promote a positive working environment. The principles of the Concordat for research integrity are embedded into the training. | The principles of the Concordat for research integrity are embedded into the training. The training provides researchers with an action plan and portfolio of reflective practice to continue their development, researchers and managers are encouraged to refer to their plans and portfolio's regularly and use as a framework to support professional conduct; aiming to achieve a 80% engagement and completion rate annually. As part of progression monitoring, prompts to discuss wellbeing will be embedded into monitoring forms and revisited annually aiming to get 70% completion and engagement from researcher, line managers and supervisory teams. | September 2020 | HR, Doctoral School | Completed. | Completed. Now embedded into the current processes. The actions plans provide realistic outputs and examples of practice that can be utilised as part of the training or sharing practice within the researcher community. | Completed | P6.9 | Completed - no further action
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | Managers are provided with guidance on university plocies and processes around flexible working requests with a focus on agile working practices to support researcher work-life balance. | This is an annual item of business at core university committee and groups, reviewed every 12 months or more frequently in-line with practice and policy changes. The research community receive regular communications on a monthly basis or more frequently through Teams group and individual emails. Visibility of a new academic handbook on intranet pages and external pages will help increase awareness. Quarterly communications aim to increase traffic to the handbook and practices by 25% | Ongoing (BAU) | HR, Doctoral School | Completed, the processes are established and in place. | Completed. The new web structure provides metrics on access to continue to monitor and access access and engagement of outputs. | Completed | New | Completed - no further action
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Identified as part of the 3 year plan process and open calls to develop research-led interventions. Linked to ECI 3 and ECM4. | This is an annual item of business at core university committee and groups, reviewed every 12 months or more frequently in-line with practice and policy changes. The research community receive regular communications on a monthly basis or more frequently, this includes regular calls to contribute and influence policy development, environment and culture through working groups and listening events, aiming to increase participation by 20% across the university community. | Completed initially but part of an ongoing process | R&E Director, Doctoral School, HR (e.g. Athena SWAN and REC committees) | Completed, the processes are established and in place. | Completed. The new web structure provides metrics on access to continue to monitor and access access and engagement of outputs. | Completed | New | Completed - no further action
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | A mentoring and support network has been established at both PGR and research staff level to encourage this behaviour. Those who are mentees are encouraged to be mentors moving forward. | Using online community environments such as Microsoft Teams, there are opportunities for researchers to actively contribute to the research culture. The community environments encourage sharing of practice, supporting newer researchers and creating communities of practice. Engagement is measured by 50% of the research community making a contribution to or by using the online communities. | October 2021 | R&E, Schools, Doctoral School | Online communities have been established through Microsoft Teams. A specific ECR Network Teams site will be set up for this community as a future action. | Complete. During the Covid lockdown, there has been greater utilisation of online communities and attendance at training increased due to the convenience of online participation. This will be kept under review in development of the new researcher training programmes for PGRs and staff when considering the balance of in-person and online support. ECR Network to be created and the community supported through online tools going forward. | As previous action | New | Taken forward in 2022-25 action plan
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | Encourage the exploration of funder policy and guidance in this area - some guidance is also provided in the supervisor training. | The induction process for new researchers sign-posts to the relevant policies and guidance. 100% completion of the induction process for PGRs is required within the first 3 months of arrival. | September 2021 | The Doctoral School and HR | Not relevant for target group. | Not relevant for target group. | As previous action | P5.3 | Not relevant for target group.
ECR3 | Take positive action towards maintaining their wellbeing and mental health | At induction and through regular campaigns, research are encouraged to consider this fully. As well as in recent Return to campus or safety working remotely provisions. | Through the return to campus and safe working remotely provision, an individual risk assessment is completed that also considers wellbeing individually and in relation to the research project. 100% completion is required and this is reviewed during monthly supervision/line management meetings. The process is reviewed annually. | October 2022 | HR, Doctoral School | Completed, the processes are established and in place. | Completed. This was added as a COVID-19 response to ensure all staff discussed return to campus needs and received necessary support. | As previous action | New | Completed - no further action
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | Policies and procedures are in place to address concerns of this nature and well communicated to all staff. | Policies and procedures are in place to address concerns of this nature and reviewed regularly. The review and update of the University of Salford’s Whistleblowing policy to ensure to the clear routes to raising any concerns or issues is to be made available on web pages and intranets. Reviewed annually. | Ongoing (BAU) | HR, Doctoral School | Completed, the processes are established and in place. | Completed. This is now available on intranets and web pages, supported with regular marketing and communications to further support. | Completed | P6.9 | Completed - no further action
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Opportunities to be identified for staff via the 3 year plans and for PGRs through the Doctoral Steering Group. | To develop a co-creation approach to support research development. This is measured by an increase in number of research-led activities and contributions to include at least one PGR 'take over' event or activity and one staff development session created by researchers to support researchers. Increase participation with such events by 30%. | August 2021 | The Doctoral School | Initial discussions underway with different research groups about prospective activities from conferences to bespoke training events for delivery in 2021. | There are a number of committees to which staff can contribute to policy development, e.g. REC, school RECs, Senate, REF Steering Group, Research Centre meetings, etc. To be taken forward as an action for the ECR Network. | As previous action | P6.9 | Taken forward in 2022-25 action plan
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | Recruitment processes supported centrally to drive consistency, recently reviewed process updated to drive a partnered approach between the recruiting manager and recruitment team. This is to ensure appropriate activity and actions taken in finding the right candidates and talent. Recruitment system is to be updated to support greater transparency and significantly improved applicant journey and further drive our inclusivity agenda. | Driven through UoS inclusivity agenda, a recruitment project to improve the recruitment experience, is underway; success is measured through candidate feedback and increasing participation from under-represented groups. Recent success has been obtained through improving UG recruitment, this could be used as model to improve PGR; aiming to increase numbers by 10%. | December 2021 | HR | Completed, the processes are established and in place. | Completed. New recruitment system has been deployed in 2022 which ensures information about applicant protected characteristics is not visible to panels during shortlisting. | As previous action | P1.2 P6.2 P6.7 | Completed - no further action
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | All PGRS and staff receive a full induction within 3 months of their start date. | This is monitored and followed up within the 3 month start date window. 100% completion required within 12 months of start date. | Completed | The Doctoral School & HR | Completed, the processes are established and in place. | Completed. Outputs are regularly reviewed as part of annual business activities and to ensure ongoing alignment with the Concordat and University objectives. | Completed | P3.6 P3.9 P5.5 | Completed - no further action
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | Researchers are part of the current reward structure of the university when they are contracted to the university. This provides pathways for progression. | Events and activities to recognise contributions are in place such as the Supervisor of the year awards, PGR awards as part of SPARC (Salford Postgraduate Annual research Conference). Pilot promotion support for research focussed staff through specific development workshops and career coaching. Success is measured through engagement by an increase in attendance by 20% compared to other development activities. | Ongoing (BAU) | HR, Director of the Doctoral School | Completed, the processes are established and in place. | Completed. Outputs are regularly reviewed as part of annual business activities and to ensure ongoing alignment with the Concordat and University objectives. | Completed | P2.6 P6.3 P6.4 P6.7 | Completed - no further action
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | Opportunities are provided through Salford Managers programme and PMO project management course and 'on demand' training through LinkedIn learning. | As above and through targeted training that utilises the data from the 3 year plans and PDR discussions. Success is measured using online platforms, altmetrics help track usage and aims to increase participation by 10% engagement. Evaluation feedback will continue to inform the training offer, gathered during/after the training and reviewed annually | Ongoing (BAU) | HR | Completed, the processes are established and in place. | Completed. Outputs are regularly reviewed as part of annual business activities and to ensure ongoing alignment with the Concordat and University objectives. | Completed | P2.3 | Completed - no further action
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | As part of our commitment to deliver the Academic Career Framework effectively, we have a wrap around programme of development and engagement activity. This includes leadership development for all line managers including how to have effective conversations around performance, development giving and receiving feedback and facing into performance conversations. We instill a consistent approach to performance conversations using the Academic Career framework and drive adoption both top down and bottom up within the teams. We have developed institional performance targets and a golden thread flows through all teams aligning to the University strategy therefore allowing all to be clear on performance and contribution. These feed talent approach and ultimately promotion opportunities using the Acadmeic career framework. | A series of high profile campaigns have been established to champion and increase awareness of the behaviours and positive research culture, aligned to key activities such as 3 year plans, the REF process, SPARC and Festival of Research. Success is measured though marketing data to establish engagement with these campaigns, aiming for 40% of the researcher community to engage through reading/clicking to targeted communication messages or registering for events. | Ongoing (BAU) | HR | Completed, the processes are established and in place. | Completed. Outputs are regularly reviewed as part of annual business activities and to ensure ongoing alignment with the Concordat and University objectives. | Completed | P2.6 P6.3 P6.4 | Completed - no further action
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | There is a Fixed Term Contract policy in place for the fair treatment of those on contracts. This policy and others will be incorporated into the review of all current policies and procedures overseen by the HR Team. | The review project is underway and this aligns to other processes to support recruitment and development. Further consultation will form part of the Festival of Research and Technicians Conference - aiming to increase participation and input into the process by 20% on previous engagement targets. | Ongoing (BAU) | HR | Completed | Completed. Policy is reviewed on a regular basis as part of BAU in HR. | As previous action | P1.3 P2.1 P2.2 | Completed - no further action
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | Researchers and the research community are heavily involved in our review processes, for example our Academic Career Framework has an annual review process to ensure it stays up to date and relevant. The research pathway is owned by the PVC for Research and Enterprise and their team review and feed in all requirements and sign it off as appropriate and fit for purpose. | The ACF and 3 year plans are readily used to support career development chats for research focussed staff. The Learning Agreement for PGRs in annually updated and reviewed to support research development. Both processes provide opportunities to enage with decisions making on an ongoing basis. In addition to this,members of the researcher community are encouraged to join the researcher dedevlopment group to specifically input into short and long-term development, policy and decision making. | Completed | RKE & HR | Completed, the processes are established and in place. | Completed. Further outputs are generated through the researcher input such as testimonies, case studies or examples of practice. To generate awareness of this and to further engage the researcher community, these outputs will be made available (with permission) to the wider researcher community. | Completed | P3.13 | Completed - no further action
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | Review of Salford offer and pricing structure underway. A bespoke training programme for funding training. | The funding offer to be in place by Nov 2020. 30% of researchers identified to focus on funding and income to have funding development plans in place by Dec 2022 | December 2022 | RKE and Collaborative partners | Action discontinued due to reprioritisation of work in line with Innovation Strategy 2021-26. | Within our redevelopment of the staff training offer there will be a focus on funding and on how researcher careers should be supported through externally funded projects. | As previous action | P2.4 | Not complete - action discontinued
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | Linked to EF1. As part of the finding training programme, include opportunities to explore sources and strategies to generate funding to secure/extend current contract. As part of this offer encourage reflection and planning on career pathways. Impact data to be collected through staff surveys and feed into the training and development agenda. | As above. The funding offer to be in place by Nov 2020. 30% of researchers identified to focus on funding and income to have funding development plans in place by Dec 2022. Impact data collected via annual staff surveys to be embedded into 3 year plan process so to encourage conversations about career progression. The Academic Career Framework (ACF) to provide clear pathways to progression and opportunities to move role within the Unversity. | December 2022 | RKE and Collaborative partners | Action discontinued due to reprioritisation of work in line with Innovation Strategy 2021-26. | Within our redevelopment of the staff training offer there will be a focus on funding and on how researcher careers should be supported through externally funded projects. | As previous action | New | Not complete - action discontinued
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | Linked to EF1&2. As above. | As above. The ACF to be embedded into development plans in place by Dec 2022.Introduction of regular School specific workshops to discuss employment and provide opportunities to develop career progression by Dec 2022. This will be measured by feedback from the researcher community on employment and development opportunities and recuitment leads on empoiyability and suitability of internal applicatnts to increase participation in both activities by 20%. | December 2022 | RKE and Collaborative partners | Action discontinued due to reprioritisation of work in line with Innovation Strategy 2021-26. | Within our redevelopment of the staff training offer there will be a focus on funding and on how researcher careers should be supported through externally funded projects. | As previous action | P2.4 | Not complete - action discontinued
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | Linked to EF1-3 as above. | As above. The dunding offer to be in place with 30% of researchers identified to focus on funding and income and to have funding development plans in place by Dec 2022 | Dec 2022 | RKE | Action discontinued due to reprioritisation of work in line with Innovation Strategy 2021-26. | Superceded by action against ECF3 relating to providing funding for different career stages on an annual basis | As previous action | New | Not complete - action discontinued
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | Through Academic Career Framework deployment we invite all line managers to go through leadership development, this coupled with the tools we share give us a more consistent approach to line management capability. | This regularly reviewed on an annual basis and through consultation with the research community, opportunities to evolve and develop support are facilitated. Training is highlighted to PGR by Supervisory team at Annual Assessment point, through self reflection in the Learning Agreement and APR, by Supervisors and their line managers in PDR processes and 3 yearly refresher training, and by support staff and their managers through the annual PDR process. 100% completion is required of all processes. | Completed | RKE & HR | Completed, the processes are established and in place. | Completed. The outputs generated from the completion of the processes is now used as part of the annual evaluation review. | Completed | P2.3 | Completed - no further action
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | Through forums and committees such as REC, AEC and PGR Forum, staff are able to engage and input into the relevant codes and policies for the University. There's further enhancement and engagement opportunities with national policy and practice through development networks such as Vitae, UKCGE and CIPD. | This is part of an ongoing commitment and now embedded into the annual life cycle of the review and update of institutional codes and policies. New funding development training to be implemented by September 2022 with 40% attendance as a measure of engagement. | Completed | RKE & HR | Completed, the processes are established and in place. | Completed. The outputs generated from the completion of the processes is now used as part of the annual evaluation review. | Completed | P2.2 | Completed - no further action
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | Look to introduce annual equality monitoring of researchers relating to reward, recruitment and promotions. | Part of a larger recruitment and support project linked to EI1 and EI6. Make the recruitment process more transparent and additional guidance provided in place for PGR by Sept 2021 with 80% of new PGRs recruited through this pathway and similar process research staff (as part of wider recruitment project) phase 1 by Sept 2022. | December 2022 | HR | Completed, the processes are established and in place. | I&D team in HR provide annual reporting on recruitment and promotions by protected characteristics for researchers; analysis of data relating to recruitment and promotion is undertaken as part of Athena Swan actions to oversee recruitment by protected characteristics | As previous action | P6.3 | Completed - no further action
EM4 | Actively engage in regular constructive performance management with their researchers | This is a fundamental part of effective line management and is an expectation of all colleagues through the Professional Development Review and career conversations. Through calibration and moderation activity we are driving a consistent approach to management allowing all teams and individuals to get the same support. | This is part of an ongoing commitment and now embedded into the research life cycle, PDR process for staff. The Vitae RDF is used in discussion between PGRs and Supervisors at monthly and annual progress meetings. Performance Development Chats to be introduced and rolled out to 50% of the researcher community by Nov 2022 | Ongoing (BAU) | HR | Completed, the processes are established and in place. | All academic researchers now participate in Performance and Career Conversations with their line managers, which is the new format for annual appraisal, launched across all schools during 21-22. | Completed | P2.3 | Completed - no further action
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | EI7, ECR5. Through forums and committees such as REC, AEC and PGR Forum, staff representation on Senate and Council, Athena Swan committee, Race Equality Charter group, staff are able to engage and input into the relevant codes and policies for the University. There's further enhancement and engagement opportunities with national policy and practice through development networks such as Vitae, UKCGE and CIPD. | Increase participation and contribution of research staff and PGRs in key groups such as research development group through engaging with line managers and supervisors. Aim to have 30% membership of the group made up of PGRs and supervisors | September 2021 |  | Partially completed - superceded by new action | Partially completed - superceded by new action. There is represetation at local (School) level and on some committees but this will be taken forward as a new action for the ECR Network. | As previous action | New | Partially completed - superceded by new action against this principle
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | For supervisors this is done through our enhanced, co created and peer led supervisor training. For PGRs, this is done through our enhanced online training provision, new Doctoral School Hub and Teams training sites, and also via their supervisors. | Expectations are set out in the SER process for PGRs on an annual basis. 100% completion by PGRs to ensure registration for following year of study. | Completed | RKE & HR | Completed, the processes are established and in place. | Completed. The outputs generated from the completion of the processes is now used as part of the annual evaluation review. | Completed | New | Completed - no further action
ER2 | Understand their reporting obligations and responsibilities | This is set out in the induction process and through the SER and 3 year plan processes | Linked to ER1 and monitored through existing processes. All new starters to complete induction and mandatory courses, aiming for 100% completion within 3 months of start date. Supervisors and line managers to complete annual reviews aiming for 90% completion (allowing for mitigation and interruptions). | Completed | RKE & HR | Completed, the processes are established and in place. | Completed. The outputs generated from the completion of the processes is now used as part of the annual evaluation review. | Completed | New | Completed - no further action
ER3 | Positively engage with performance management discussions and reviews with their managers | 3 year plans and PDRs for staff and monthly supervisor meetings and SER for students. | Linked to ER1 & 2 and monitored through existing processes. Engagement measured through completion and annual evaluations aiming to for 50% respondent rate to evaluate engagement. | Completed | RKE & HR | Completed, the processes are established and in place. | Completed. Outputs generated could be utilised to share practice moving forward. | Completed | P5.6 | Completed - no further action
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | Promotion of Academic Citizenship through the PGR seminar series and ACP for students, mentoring and SRR for staff. | Rewarding 'Citizenship' and being part of the academic community. Measurement of success is in evaluating collective engagement e.g. increase in participation and frequency in community activities such as the Festival of Research and increasing participation by 10% annually. | Completed | RKE & HR | Completed, the processes are established and in place. | Completed. Outputs generated could be utilised to share practice moving forward. | Completed | P5.2 | Completed - no further action
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | A range of core research development activities such as research development days, FoR and SPARC make up a common core of 10 days with additional shorter training events throughout the year as part of the research development offer. | This regularly reviewed on an annual basis and through consultation with the research community, opportunities to evolve and develop support are facilitated. Reviews are mapped to the RDF for PGRs and ACF for RFS and time is provided through regular 'thinking and writing retreats' to continue meaningful career development in the longer term. Retreats to be in place by Sept 2021. The structured support to include mentorship across academica and industry or enterprise as part of the researcher development programme, in place by Sept 2021. | Ongoing (BAU) | Researcher Development Manager, Doctoral School | Completed, the processes are established and in place. | Completed. Various touch points to encourage 'chats' at regular intervals are now embedded into processes such as PDR, Learning Agreements and this is supported by an annual career development symposium for researchers (taking place annually in January and aligned with PDRs). | Completed | P3.1 P3.3 P5.5 | Completed - no further action
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | Training support, drop-in sessions and 'retreats' where there's the opportunity to actively progress work in a structured way is available. SRR has provided staff with time to focus and commit to their development. | This regularly reviewed on an annual basis and through consultation with the research community, opportunities to evolve and develop support are facilitated. Reviews are mapped to the RDF for PGRs and ACF for RFS and time is provided through regular 'thinking and writing retreats' to continue meaningful career development in the longer term. Retreats to be in place by Sept 2021 | Completed | HR | Completed, the processes are established and in place. | Completed. Various touch points to encourage 'chats' at regular intervals are now embedded into processes such as PDR, Learning Agreements and this is supported by an annual career development symposium for researchers (taking place annually in January and aligned with PDRs). | Completed | P3.10 | Completed - no further action
PCDI 3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | This is provided through the doctoral school hub, student and staff hubs with an annual careers symposium for research and research careers. | Co-created and peer led training content and delivery helps to ensure provision is fit for purpose and continues to be reviewed and revised regularly through embedded processes. Annual career development conferences will provide opportunities to access professional advice on career development. An opportunities to revisit career developmt is provided in regular 121 career development chats in place by Feb 2021. | Completed | Researcher Development Manager, Doctoral School | Completed, the processes are established and in place. | Completed. Various touch points to encourage 'chats' at regular intervals are now embedded into processes such as PDR, Learning Agreements and this is supported by an annual career development symposium for researchers (taking place annually in January and aligned with PDRs). | Completed | P3.1 | Completed - no further action
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | Utilising the BAU support we give for all colleagues such as Salford conversations, Leading at Salford and more uniquely the Academic career framework for researchers. As part of deployment of Academic career framework we have implemented a more holistic conversation performance and career conversation driving a holistic conversation about performance, development, workload, and wellbeing meaning we can support individuals needs. PGR seminar series, mentoring and ACP for students. | Co-created and peer led training content and delivery helps to ensure provision is fit for purpose and continues to be reviewed and revised regularly through embedded processes. In place by Feb 2021 and reviewed annually. | Completed | Researcher Development Manager, Doctoral School | Completed, the processes are established and in place. | Completed. Now embedded into the various plans and progress monitoring tools. The main outcome is that thie will assist with monitoring moving forward whilst also supporting researchers to increase their development portfolio. | Completed | P3.11 P3.14 | Completed - no further action
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | External mentoring with other HEI's and Industries available for students and staff. Linked to PCDR2. | Development of a stream of activities and opportunities for researchers to frequently engage and experience employability and networking specifically for research. These activities to be piloted and embedded into training and development provisions by mid 2021. | 2021-04-01 | Researcher Development Manager, Doctoral School | Internal provisions and mentoring in place such as SARMS. MCR mentoring across institutions and support for networking is underway and on schedule. | Completed (MCRM: https://mcrmentoringprogrammenw.wordpress.com/ and SaRMS https://testlivesalfordac.sharepoint.com/sites/SalfordResearchmentoringScheme/SitePages/Salford-Research-Mentoring-Scheme.aspx?web=1 | As previous action | P3.2 P3.4 | Completed - no further action
PCDI 6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and research career development reviews | Engagement is monitored and part of an annual reporting process. | Embedded into research lifecycle and recorded through the learning agreement, SER, 3 year plan and PDR process. Regular opportunities are facilitated and encouraged and the overall process is now embedded. This is reviewed annually, monitored and updated as appropriate. This is monitored via annual reviews in place by Mar 2021. | Ongoing (BAU) | Researcher Development Manager, The Doctoral School and HR | Completed, the processes are established and in place. | Completed. Now embedded into the various plans and progress monitoring tools. The main outcome is that thie will assist with monitoring moving forward whilst also supporting researchers to increase their development portfolio. | Completed | New | Completed - no further action
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | This is a core part of the training and development offer with a specific stream on accessing and progressing research funding. Linked to ECF1-3. | Continue to work with funding organisations (including industry, research councils, charities and consortiums to co-create a positive research culture and environment). This includes regular consultation with the research community and partner funders to take place on an annual basis. Provide workshops to evidence development such as career planning and application workshops as part of the researcher development programme, in place by Sept 2021. Engagement measured against number of opportunities taken as part of 10 development days quota, aiming for 20% of researcher community engagement. | 2022-07-01 | RKE and Collaborative partners | Initial meetings took place as part of the 2018 and 2019 Festival of Research. This included the development of a Future of Research output publication: Reimagining: https://usir.salford.ac.uk/49241/. The 2020 event was postponed by Covid but will continue in 2021 either in person or as an online event. | Completed. This is now being embedded into the various PDR, plans and progress monitoring tools. Other outcomes such as pathways to navigate development have also been implmented to support this activity. | As previous action | P3.7 P3.9 | Completed - no further action
PCDF2 | Embed the Concordat Principles and research development into research assessment strategies and processes | These are embedded into the SER (process for PGRs) and as part of the ACF for staff and their 3 year plans. This is also linked to ECF1-3. | Continue to work with funding organisations (including industry, research councils, charities and consortiums to co-create a positive research culture and environment). This includes regular consultation with the research community and partner funders to take place on an annual basis. The Concordat principles to be referenced and linked to on annual review forms and the newly revised web pages in place by July 2021. | Ongoing (BAU) | RKE and Collaborative partners | Initial meetings took place as part of the 2018 and 2019 Festival of Research. This included the development of a Future of Research output publication: Reimagining: https://usir.salford.ac.uk/49241/. The 2020 event was postponed by Covid but will continue in 2021 either in person or as an online event. | HR, R&E and the Library ensure research assessment mechanisms support researcher development and that the use of metrics is appropriate in line with our commitment to DORA. | As previous action | New | Completed - no further action
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | Through identifying this in 3 year plans, the Academic Career Framework will build skills both valuable in and out of the Academic sphere of work. Through PGR specific career related activities including the careers symposium. Linked to ECF1-3. | Continue to work with funding organisations (including industry, research councils, charities and consortiums to co-create a positive research culture and environment). This includes regular consultation with the research community and partner funders to take place on an annual basis. Additional support as an annual career development conference implemented across both PGR and research staff communities by Sept 2022, engaging with at least 20% of the researcher community. | 2022-07-01 | RKE and Collaborative partners | Initial meetings took place as part of the 2018 and 2019 Festival of Research. This included the development of a Future of Research output publication: Reimagining: https://usir.salford.ac.uk/49241/. The 2020 event was postponed by Covid but will continue in 2022 either in person or as an online event. | Completed. Already included in careers events provided for PGRs and new activity will continue this for ECRs and wider academic community. | As previous action | New | Completed - no further action
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | Embedded through 3 year plans, PDR for staff and SER, learning agreements and assessment points for students. Deployment of Academic Career Framework takes all line managers through leadership development to have effective performance conversations with their teams. | Embedded into research lifecycle and recorded through the learning agreement, SER, 3 year plan and PDR process. Regular opportunities are facilitated and encouraged and the overall process is now embedded. This is reviewed annually, monitored and updated as appropriate. | Ongoing (BAU) | The Doctoral School and HR | Completed, the processes are established and in place. | Completed. Various touch points to encourage 'chats' at regular intervals are now embedded into processes such as PDR, Learning Agreements and this is supported by an annual career development symposium for researchers (taking place annually in January and aligned with PDRs). | Completed | P2.3 | Completed - no further action
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | Sign posting to resources such as mentoring and careers. | Embedded into research lifecycle and recorded through the learning agreement, SER, 3 year plan and PDR process. Regular opportunities are facilitated and encouraged and the overall process is now embedded. This is reviewed annually, monitored and updated as appropriate. The cross institutional mentoring scheme is available from spring 2021 aiming for 10% of the research staff community to apply. | Ongoing (BAU) | The Doctoral School and HR | Completed, the processes are established and in place. | Completed. The mentoring schemes are progressing well and early outcome indicate that the programme and ability to 'shape it' have increased engagement with the development agenda. | Completed | P3.4 P3.8 P5.5 | Completed - no further action
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | This is allocated as mentioned above. | Embedded into research lifecycle and recorded through the learning agreement, SER, 3 year plan and PDR process. Regular opportunities are facilitated and encouraged and the overall process is now embedded. This is reviewed annually, monitored and updated as appropriate. Regular opportunities to connect with the researcher community and onward development monthly. | Ongoing (BAU) | The Doctoral School and HR | Completed, the processes are established and in place. | Completed. The 10 days development is now embedded into the various PDR, plans and progress monitoring tools. Other outcomes such as pathways to navigate development have also been implmented to support this activity. | Completed | New | Completed - no further action
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | This is allocated as mentioned above. | Embedded into research lifecycle and recorded through the learning agreement, SER, 3 year plan and PDR process. Regular opportunities are facilitated and encouraged and the overall process is now embedded. This is reviewed annually, monitored and updated as appropriate. Development opportunities to be circulated to the researcher community on a bi-weekly basis or more frequently, with at least 24 communications per year. | Ongoing (BAU) | The Doctoral School and HR | Completed, the processes are established and in place. | Completed. The 10 days development is now embedded into the various PDR, plans and progress monitoring tools. Other outcomes such as pathways to navigate development have also been implmented to support this activity. | Completed | P3.6 P3.9 P5.5 | Completed - no further action
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | All line managers as part of Academic career framework go through specific line manager leadership development activity to build the capability to have effective conversations. | Further embedding to support leadership and training through the exploration of additional qualifications to evidence employability and personal transferable skills to be in place by Sep 2021. | September 2021 | The Doctoral School and HR | Completed, the processes are established and in place. | Completed. The ACF is now in use for all schools and provides a clear pathway for development and progression, supported by demonstrable outputs. Organisational Development in HR provides Salford Manager training to support professional development The Salford Manager course to be used as the basis for future ECR-specific training for those who supervise/oversee others. | As previous action | New | Completed - no further action
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | Encouraged through PDR, Learning agreement. A toolkit of resources are available including careers checklist, skills audits and reflective practice events. | This is embedded into the PGR lifecycle and annually followed up prior to re-registration or thesis submission. For all staff, this is part of the PDR process and 3 year development plans, also reflected on annually. | 2020-05-01 | The Doctoral School | Completed | Completed. The 10 days development is now embedded into the various PDR, plans and progress monitoring tools. Other outcomes such as pathways to navigate development have also been implmented to support this activity. | Completed | P5.5 | Completed - no further action
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | In place as part of SPoRT and SECRET programmes, including SARMs (Salford Academic Research Mentoring) programme for research focussed staff and the Academic Citizenship Programme for PGR Students. | Additional initiatives to support current practice including interinstitutional mentoring for mid-career research staff and cross-institutional PGR networking for Doctoral researchers. A specific mid-career researcher programme to be implemented by May 2021. | April 2021 | The Doctoral School | Completed | Not relevant for target group. | As previous action | P3.8 | Not relevant for target group.
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | For PGRs - this is provided through the learning agreement and SER. For staff this is within the 3 year plans and PDR. Linked PCDR1. | Embed the LA and SER into the PGR lifecycle and make access to Advantage download/transcripts more accessible and increase awarenss as part of the inaugral Festival of Research. The 3 year plans aligned with the PDR process ahead of submission of the REF environemnt statement submission by Dec 2022. | March 2018 | RKE | Completed | Completed. These outcomes and portfolio is available through repositories such as Figshare and ORCID. | Completed | P5.5 | Completed - no further action
PCDR4 | Positively engage in career development reviews with their managers | Prompted as part of above processes: PCDR1-3. | Engagement tracked through the number of submissions. Career development conversations encouraged as part of annual review processes, aiming for 80% completion of 'career development' related sections of annual reviews, learning agreements and other online monitoring forms, reviewed annually. | March 2018 | RKE | Completed | Completed. Through the outcomes of these actions, and tracking back to 2018, a story of change is developing. Rather than just tracking engagement, more researchers are directing it and not just actiing as 'consumers' but as 'activists' of change, taking a more pro-active and citizenship-based role within the researcher community with many more researchers contributing to theresearcher development agenda. | Completed | P3.10 | Completed - no further action
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Prompted as part of above processes: PCDR1-3. | Engagement is tracked through number of ORCID profiles (aiming to increase number of profiles by 20%) and engagement with initiatives such as small grants and Festival activities (increase in participants by 10%). | September 2021 | The Doctoral School | Completed | Not relevant for target group. | As previous action | P5.5 | Not relevant for target group.
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | Prompted as part of above processes: PCDR1-3 and PCDR 5. | As above, engagement is tracked through 20% increase in number of ORCID profiles and initiatives such as small grants and Festival activities. The number of PGRs taking up PE opportunities with The Brilliant Club will also be used to measure awareness and tracking of key words in relation to knowledge exchange, policy, PE and commercialisation as part of the 3 year year plan review process. PGRs participating with the Brilliant Club increase to 10% by Sept 2022. | September 2022 | Researcher Development Manager (and R&E teams) | Completed | Not relevant for target group. | As previous action | P5.2 | Not relevant for target group.